## Sprint 1 — Foundation & Core AI
Sprint Retrospective — Sprint 1 — Foundation & Core AI Pipeline
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints.
Both CNN models (ResNet18 insect classifier and EfficientNet-B0 rice disease model) were successfully trained and integrated into the Flask inference server within the sprint window, achieving best validation accuracies of 87.24% and 86.06% respectively. The React-to-Flask image upload pipeline worked correctly on the first integration test — no CORS or encoding issues encountered. Supabase authentication and Row Level Security (RLS) policies were configured correctly, ensuring user-scoped data access from day one. All 4 committed user stories (#US01–#US04) were completed within the sprint window with a 100% completion rate. Daily stand-ups were productive and helped surface blockers early — the team resolved the checkpoint-loading latency issue within 24 hours of identifying it. | Initial model serving loaded PyTorch checkpoints on every POST request, causing inference latency spikes of 3–5 seconds per request. Decision rules (disease class → chemical recommendation) were hardcoded in the React frontend JavaScript, making them difficult to update without a code deploy. The dataset used for training (PlantVillage) consists primarily of controlled lab-condition images, which limits real-world generalization to complex field backgrounds and varying lighting conditions. | Load both model checkpoints into memory once at Flask server startup to eliminate per-request loading overhead. Migrate all decision rules (class → chemical, dosage, notes) to a dedicated spray_recipes table in Supabase so they can be updated via an admin UI without code changes. Augment the training dataset with field-collected images featuring complex backgrounds, varied lighting, and partial occlusion to improve model generalization. Apply Temperature Scaling (T parameter) post-training to calibrate model confidence scores and reduce overconfident predictions. | DONE: Modified Flask serve.py to load both checkpoints on startup and cache them in memory — latency reduced from 3–5s to under 1s per request. PLANNED (Sprint 2): Create spray_recipes Supabase table with columns: model_id, class_label, action_type, recommendation, dosage, min_confidence, special_notes. Build Admin Rules panel (Rules.tsx) for CRUD operations. PLANNED (Sprint 3): Apply Temperature Scaling T=1.8 in Flask server. Collect additional field images and augment with RandomPerspective, ColorJitter, GaussianBlur, and RandomErasing transforms.

## Sprint 2 — Platform Features &
Sprint Retrospective — Sprint 2 — Platform Features & Analytics
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints.
The Analytics Dashboard rendered accurately from live Supabase data on the first full integration test — the database aggregation query and Recharts rendering pipeline was correctly implemented without debugging. The JWT middleware (requireAuth) enforced authentication cleanly across all 5 API routes — unauthorized requests returned 401 Unauthorized without leaking data. The Spray Schedule completion workflow (counter increment + next spray date recalculation) worked correctly through multiple mark-done cycles in testing. Weather widget data from OpenWeatherMap loaded within 2 seconds, with graceful fallback text when the API timed out. All 6 committed user stories (#US05–#US10) were completed — 100% completion rate. The History page's real-time search filtering delivered a noticeably better user experience compared to a server-side pagination approach. | The Spray Schedules page initially required a completed diagnosis to create a schedule — there was no way to manually add a schedule entry independently. The analytics confidence distribution histogram required additional CSS debugging to render consistently across 375px mobile viewports and 1440px desktop viewports. The OpenWeatherMap free tier has a rate limit of 60 calls/minute; during load testing with multiple simultaneous users, rate-limit errors (HTTP 429) were occasionally triggered. Setting up the Express server as a Vite proxy required careful configuration — early tests had the proxy routing incorrectly, causing 404 errors on all /api routes. | Allow manual schedule creation from the Spray Schedules page directly, independent of a prior diagnosis, so farmers can schedule preventive treatments. Add a server-side cache (in-memory or Redis) for weather API responses with a 10-minute TTL to reduce OpenWeatherMap API calls and avoid rate limits. Implement a progressive loading strategy for the Analytics Dashboard — show skeleton cards while data loads rather than a blank page. Add a plant tracking module (Plants page) so farmers can link diagnoses to specific named plant records and track health over time. | DONE: Wired 'Create Spray Schedule' button directly to the diagnosis result panel so a schedule is auto-created from the recommendation — no separate manual entry needed. DONE: Fixed CSS media queries for analytics histogram — tested on Chrome DevTools at 375px, 768px, and 1440px breakpoints. PLANNED (Sprint 3): Add Plants.tsx page with plant name, crop type, and health score linked to diagnosis records. PLANNED (future): Implement weather response caching with a 10-minute TTL to handle multiple concurrent users without hitting rate limits.

## Sprint 3 — Multi-Model Integrat
Sprint Retrospective — Sprint 3 — Multi-Model Integration & Finalization
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints.
All three AI model endpoints (MobileNetV2 local, HuggingFace Rice Disease, HuggingFace EfficientNet-B0 Pest) integrated correctly from the single POST /api/roboflow/infer router on the first integration test. Temperature Scaling (T=1.8) visibly improved confidence score realism — predictions that previously returned 100% confidence now return calibrated 70–95% scores, making the system more trustworthy for farmers. The three-state badge logic (Action Required / Healthy / Review) correctly distinguished all possible diagnosis outcomes across all 18 class-recipe combinations. The Admin Rules Panel enabled non-technical users to reconfigure spray dosages and chemicals without any database access — a key usability milestone. All 4 committed user stories (#US11–#US14) completed — 100% completion rate. PDF report generation with jsPDF worked correctly on first integration, producing clean reports with the crop image, diagnosis, dosage, and notes. | HuggingFace free-tier Spaces experience 30–60 second cold starts after periods of inactivity, causing user-facing timeouts on the first request after an idle period. The IoT sprinkler module is simulation-only — it logs actions to the console but does not send real signals to physical hardware, limiting demonstration realism. The MobileNetV2 local model was trained on controlled PlantVillage images; in real-world field tests with complex backgrounds, some misclassifications were observed for tomato early blight vs. septoria leaf spot. The PDF report layout required multiple jsPDF iteration cycles to correctly position the crop image thumbnail alongside the text columns. | Implement a keep-alive ping mechanism (scheduled HTTP GET to /health endpoints every 4 minutes) to prevent HuggingFace Space cold starts during active sessions. Replace the IoT simulation with real MQTT broker integration (e.g., HiveMQ or Mosquitto) and a Raspberry Pi GPIO controller for physical sprinkler hardware. Expand the training dataset with field-collected rice and tomato images using transfer learning with domain adaptation to improve real-world accuracy. Add a mobile-first Progressive Web App (PWA) offline mode so farmers can view their last diagnosis result even without internet connectivity in the field. Integrate a multi-language support layer (Tamil, Hindi, Telugu) to increase accessibility for non-English-speaking farmers in rural South India. | DONE: all_scores EfficientNet response parser implemented in normalizePredictions() to handle both array-based (MobileNetV2) and dict-based (EfficientNet) formats. DONE: Master SQL migration 0008_master_recipes.sql centralizes all 18 spray recipes across 3 models — single source of truth for the decision engine. DONE: GitHub repository pushed with full README, architecture diagram, LaTeX report, SQL migrations, and ML pipeline scripts. PLANNED (future): Implement HuggingFace keep-alive ping in the Express server as a scheduled cron job (every 4 minutes during working hours). PLANNED (future): Physical MQTT integration with Raspberry Pi for IoT sprinkler — requires hardware procurement and MQTT broker configuration.